## Cronograma de projeto
Python Reports Project
COMPANY NAME |  | ICM COMPUTER | [5 empty] | ENGINEER |  |  |  |  | HOURS | [19 empty] | PHASE |  |  |  |  | HOURS
DATA |  | 2024-09-19 | [5 empty] | Nicolas |  |  |  |  | 315 |  |  | 69.38% |  |  |  | Nicolas | 315 | [11 empty] | Phase 1 |  |  |  |  | 192 |  |  | 42.29% |  |  | Phase 1 | 192
PROJECT NAME |  | PYTHON REPORTS | [5 empty] | Darren |  |  |  |  | 95 |  |  | 20.93% |  |  |  | Darren | 95 | [11 empty] | Phase 2 |  |  |  |  | 48 |  |  | 10.57% |  |  | Phase 2 | 48
PROJECT REF |  | 80002 | [5 empty] | Derek |  |  |  |  | 40 |  |  | 8.811% |  |  |  | Derek | 40 | [11 empty] | Phase 3 |  |  |  |  | 52 |  |  | 11.45% |  |  | Phase 3 | 52
PROJECT LEADER |  | Pearse | [5 empty] | Paul H |  |  |  |  | 4 |  |  | 0.8811% |  |  |  | Paul H | 4 | [11 empty] | Phase 4 |  |  |  |  | 42 |  |  | 9.251% |  |  | Phase 4 | 42
TOTAL HOURS |  | 454 | [5 empty] | Steve |  |  |  |  | 0 |  |  | 0% |  |  |  | Steve | 0 | [11 empty] | Phase 5 |  |  |  |  | 50 |  |  | 11.01% |  |  | Phase 5 | 50
START DATE |  | 2024-09-20 | [5 empty] | TOTAL |  |  |  |  | 454 | [6 empty] | TOTAL | 454 | [11 empty] | Phase 6 |  |  |  |  | 70 |  |  | 15.42% |  |  | Phase 6 | 70
TARGET DATE |  | 2024-11-28 | [30 empty] | TOTAL |  |  |  |  | 454
[8 empty] | SEP | [7 empty] | OCT | [22 empty] | NOV
[8 empty] | TUE | FRI | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON | TUE | WED | THU | FRID | MON
PHASE | GOAL |  |  | TASKS | Engineer | Hours | Days | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 32 | 35 | 36 | 37
| Target start date: |  | 2024-09-23
1 | Initial Demo |  | 1 | To create a left menu | Nicolas | 50 | 7 | bar: SEP TUE to SEP MON
|  |  | 1 | To create a left menu | Darren | 4 | 2 | bar: SEP TUE to SEP WED
|  |  | 2 | Review and optimize Left Menu | Nicolas | 12 | 2 | OCT TUE: Review
| Develop a prototype featuring key reports, interactive widgets, and dynamic visualizations. The goal is to validate functionality and the visual interface, ensuring they surpass SSRS limitations. |  | 2 | Review and optimize Left Menu | Darren | 12 | 2 | OCT TUE: Review
|  |  | 3 | Be able to open SSRS from left menu on a new tab | Nicolas | 35 | 5 | bar: OCT THU to OCT WED
|  |  | 3 | Be able to open SSRS from left menu on a new tab | Darren | 8 | 2 | bar: OCT TUE to OCT WED
|  |  | 4 | Review and optimize Hyperlinnk to SSRS | Nicolas | 12 | 3 | OCT THU: Review
|  |  | 4 | Review and optimize Hyperlinnk to SSRS | Darren | 12 | 3 | OCT THU: Review
|  |  | 5 | To create a dashboard to explore the rich features available | Nicolas | 35 | 5 | bar: OCT MON to OCT FRID
|  |  | 6 | To test the app and evaluate potential issues or areas that may require attention | Nicolas | 4 | 1 | bar: OCT MON
|  |  | 6 | To test the app and evaluate potential issues or areas that may require attention | Darren | 4 | 1 | bar: OCT MON
|  |  | 6 | To test the app and evaluate potential issues or areas that may require attention | Derek | 4 | 1 | bar: OCT MON
|  |  | 7 | To present the Python Reports Prototype | bar: OCT TUE
| Phase 1 |  |  |  | Total | 192
| Target start date: |  | 2024-10-23
2 | Review and Feedback Phase |  | 1 | Translate the feedbacks and work on requested changes | Nicolas | 30 | 5 | bar: OCT WED to OCT WED
|  |  | 2 | Review and optimize changes | Nicolas | 4 | 1 | bar: OCT WED
| Collect feedback on the prototype, adjust functionalities and interface based on received comments and revisions. |  | 2 | Review and optimize changes | Darren | 4 | 1 | bar: OCT WED
|  |  | 3 | Test and get ready to present the update application | Nicolas | 7 | 1 | bar: OCT THU
|  |  | 4 | Last review before presentation after requested changes | Nicolas | 1 | 1 | bar: NOV FRID
|  |  | 4 | Last review before presentation after requested changes | Darren | 1 | 1 | bar: NOV FRID
|  |  | 4 | Last review before presentation after requested changes | Derek | 1 | 1 | bar: NOV FRID
| Phase 2 |  |  |  | Total | 48
| Target start date: |  | 2024-11-02
3 | Template Creation and Testing |  | 1 | To create a report template for new reports | Nicolas | 21 | 3 | bar: NOV MON to NOV WED
|  |  | 2 | To create a .bat file for instalation | Nicolas | 5 | 1 | bar: NOV THU
| Develop templates for future reports to standardize visuals and interactions, prepare an on-premises installation package for local use, and estimate the time needed to create new reports from Python templates compared to generating current SSRS reports. |  | 3 | Review and optimize report template | Nicolas | 7 | 1 | bar: NOV FRID
|  |  | 3 | Review and optimize report template | Darren | 7 | 1 | bar: NOV FRID
|  |  | 4 | Review and optimize .bat file instalation, test the instlation file | Nicolas | 4 | 1 | bar: NOV MON
|  |  | 4 | Review and optimize .bat file instalation, test the instlation file | Paul H | 4 | 1 | bar: NOV MON
|  |  | 4 | Review and optimize .bat file instalation, test the instlation file | Darren | 4 | 1 | bar: NOV MON
| Phase 3 |  |  |  | Total | 52
| Target start date: |  | 2024-11-10
4 | Versioning control |  | 1 | Azure DevOps project setup for version control | Nicolas | 7 | 1 | bar: NOV TUE
|  |  | 1 | Azure DevOps project setup for version control | Derek | 7 | 1 | bar: NOV TUE
| Implement version control for the project in Azure DevOps to enable efficient project management, code deployment, and version tracking. |  | 1 | Azure DevOps project setup for version control | Darren | 7 | 1 | bar: NOV TUE
|  |  | 2 | Process established for deploying Python Reports | Nicolas | 7 | 1 | bar: NOV WED
|  |  | 2 | Process established for deploying Python Reports | Darren | 7 | 1 | bar: NOV WED
|  |  | 2 | Process established for deploying Python Reports | Derek | 7 | 1 | bar: NOV WED
| Phase 4 |  |  |  | Total | 42
| Target start date: |  | 2024-11-10
5 | Testing and Quality Assurance (QA) |  | 1 | Integration testing to validate compatibility with datasets, databases, conexions etc. | Nicolas | 21 | 3 | bar: NOV THU to NOV FRID
|  |  | 2 | Integration testing to validate compatibility with datasets, databases, conexions etc. | Darren | 4 | 1 | bar: NOV FRID
| Conduct extensive testing to ensure system reliability and performance. This phase includes integration, performance, and user acceptance testing |  | 2 | Performance testing on live dev and site data | Nicolas | 7 | 1 | bar: NOV MON
|  |  | 2 | Performance testing on live dev and site data | Darren | 7 | 1 | bar: NOV MON
|  |  | 2 | Performance testing on live dev and site data | Derek | 7 | 1 | bar: NOV MON
|  |  | 5 | User Acceptance Testing (UAT) to gather feedback from end-users | Nicolas | 4 | 1 | bar: NOV TUE
| Phase 5 |  |  |  | Total | 50
| Target start date: |  | 2024-11-18
6 | Monitoring and Logging |  | 1 | Logging system to track errors and report usage | Nicolas | 21 | 3
|  |  | 1 | Logging system to track errors and report usage | Darren | 7 | 2
| Set up monitoring and logging mechanisms to track errors, performance metrics, and user activity after deployment |  | 1 | Logging system to track errors and report usage | Derek | 7 | 2
|  |  | 2 | Performance monitoring system | Nicolas | 21 | 3
|  |  | 2 | Performance monitoring system | Darren | 7 | 2
|  |  | 2 | Performance monitoring system | Derek | 7 | 2
| Phase 6 |  |  |  | Total | 70
Note on C16: Nicolas Da Silva: 1. Initial Demo Phase Description: Develop a prototype featuring key reports, interactive widgets, and dynamic visualizations. The goal is to validate functionality and the visual interface, ensuring they surpass SSRS limitations. Deliverables: - Functional prototype with dynamic and interactive reports. - Charts and tables based on data extracted through existing stored procedures. - Simplified interface with optimized navigation.
Note on G32: Nicolas Da Silva: Collect feedback on the prototype, adjust functionalities and interface based on received comments and revisions

## Sheet1
Engineer
Nicolas
Darren
Derek
Paul H
Steve
Pearse